## Sheet1
RiskAssessment - QuizedUp
| Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
1 | Broken version of app deployed to production | Deployed product may miss some requirements | Medium | High | Developer | Revert production to most recent stable version. This may mean not all features get released at the same time. | Robust unit and integration tests. Ensure API calls work and data persisted in the database.
2 | Delayed release due to code writing and/or testing take longer than anticipated | App not meeting deadline | Medium | High | Developer | Negotiate deadline if/when seeing this likelihood | Prioritise main CRUD features, ensuring they work properly before working on enhanced features.
3 | PC crash and can't reboot | App won't run if PC crashes as it runs locally | Low | High | Developer/Assessor | Application was built to the required specs. No further action required at this stage. | App can be deployed in a VM in future
4 | Inadequate app testing | Application not rigorously tested | Low | High | Developer | Present features in the application have been properly tested | Enhanced testing will be required as the app evolves.
5 | Market saturation | Application not needed | Medium | Low | None | Carry on the work | App will be donated to teachers in under-resourced countries
6 | End users not involved | Features don't meet users' needs | Low | Low | Developer & product manager | Application currently contains basic CRUD methods needed in any application. | Future iteration of app should involve end users